## Syncarpha Northbridge 1 - Batte
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-58 | 41185 | Syncarpha Northbridge 2 - Battery | Genbright LLC | 15142 | Syncarpha Northbridge 2 - Battery | Incremental Capacity | 1.666 | 1.666 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-05-22 | 2020-12-10 | 2020-12-11 | 2020-12-24 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Site Plan Approval | Town of Northbridge | MA | 2018-05-11 | 2018-08-15
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-05-18 | 2018-08-15
CPS - Financing | Source Name | Amount | Date Finance Secured
| Firstar Development | 607166 | 2019-06-01
| SPME Solar IV, LLC | 1775588 | 2019-01-01
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| BYD | CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | 2020-06-12 | 2020-09-10
| Inverter | CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | 2020-06-12 | 2020-09-10
| SU Transformer | TBD | 2020-08-31 | 2020-09-25 | 2020-11-01
| Revenue Quality Meter | Schweitzer Engineering Laboratories - SEL-735 | 2020-08-31 | 2020-09-25 | 2020-11-01
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Site Plan Approval/Town of Northbridge/MA | 2018-05-11 | Date when permit application is to be submitted | 2018-07-10 - Northbridge I - Site Plan Approval.pdf
| Site Plan Approval/Town of Northbridge/MA | 2018-08-15 | Date when permit application is to be approved | 2018-07-10 - Northbridge I - Site Plan Approval.pdf
| Order of Conditions/town of Northbridge Conservation Commission/MA | 2018-05-18 | Date when permit application is to be submitted | 2018-08-15 - Northbridge I - Order of Conditions (Recorded).pdf
| Order of Conditions/town of Northbridge Conservation Commission/MA | 2018-08-15 | Date when permit application is to be approved | 2018-08-15 - Northbridge I - Order of Conditions (Recorded).pdf
| Firstar Development/607166 | 2019-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge I Battery.pdf
| SPME Solar IV, LLC/1775588 | 2019-01-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge I Battery.pdf
| BYD/CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| BYD/CS40HN-B2428-U-R1 (Battery) | 2020-06-12 | Date when equipment is scheduled to be delivered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2020-06-12 | Date when equipment is scheduled to be delivered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| BYD/CS40HN-B2428-U-R1 (Battery) | 2020-09-10 | Date when equipment is scheduled to be tested | 2019-12-12 - Independent Engineer Mechanical Completion Certificate - Northbridge I - DNV GL.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2020-09-10 | Date when equipment is scheduled to be tested | 2019-12-12 - Independent Engineer Mechanical Completion Certificate - Northbridge I - DNV GL.pdf
| SU Transformer/TBD | 2020-08-31 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| SU Transformer/TBD | 2020-09-25 | Date when equipment is scheduled to be delivered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| SU Transformer/TBD | 2020-11-01 | Date when equipment is scheduled to be tested | 2019-12-12 - Independent Engineer Mechanical Completion Certificate - Northbridge I - DNV GL.pdf
| Revenue Quality Meter/TBD | 2020-08-31 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| Revenue Quality Meter/TBD | 2020-09-25 | Date when equipment is scheduled to be delivered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| Revenue Quality Meter/TBD | 2020-11-01 | Date when equipment is scheduled to be tested | 2019-12-12 - Independent Engineer Mechanical Completion Certificate - Northbridge I - DNV GL.pdf
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Battery | SMANG_00318 | 4
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Northbridge 1 - Solar
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-55 | 41177 | Syncarpha Northbridge 1 -Solar | Genbright LLC | 15139 | Syncarpha Northbridge 1 - Solar | Incremental Capacity | 2.764 | 0 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-05-22 | 2021-01-18 | 2021-02-26 | 2021-03-01 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Site Plan Approval | Town of Northbridge | MA | 2018-05-11 | 2018-08-15
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-05-18 | 2018-08-15
CPS - Financing | Source Name | Amount | Date Finance Secured
| Firstar Development | 6747740 | 2018-06-01
| SPME Solar IV, LLC | 12985256 | 2018-01-01
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Sungrow | Model #: SG60KU-M | 2019-07-01 | 2019-10-31 | 2020-11-30
| Inverters | Sungrow SG60KU-M | 2020-08-31 | 2020-11-16 | 2020-11-30
| Step Up Transformer | GE Prolec, 2500.750 kVA | 2021-01-04 | 2021-02-15 | 2021-02-26
| Revenue Quality Meter | Elkor Watts-On Mark II | 2021-01-04 | 2021-02-15 | 2021-02-26
| Revenue Quality Meter | Schweitzer Engineering Laboratories - SEL-735 | 2021-01-04 | 2021-02-15 | 2021-02-26
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Site Plan Approval/Town of Northbridge/MA | 2018-05-11 | Date when permit application is to be submitted | 2018-07-10 - Northbridge I - Site Plan Approval.pdf
| Site Plan Approval/Town of Northbridge/MA | 2018-08-15 | Date when permit application is to be approved | 2018-07-10 - Northbridge I - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-05-18 | Date when permit application is to be submitted | 2018-08-15 - Northbridge I - Order of Conditions (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-15 | Date when permit application is to be approved | 2018-08-15 - Northbridge I - Order of Conditions (Recorded).pdf
| Firstar Development/6747740 | 2018-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge I Solar.pdf
| SPME Solar IV, LLC/12985256 | 2018-01-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge I Battery.pdf
| Sungrow/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| Sungrow/Model #: SG60KU-M | 2019-10-31 | Date when equipment is scheduled to be delivered | 2019-07-05 - Syncarpha Northbridge I - ENGIE - PO - (ARC PO#2019-007).pdf
| Sungrow/Model #: SG60KU-M | 2020-11-30 | Date when equipment is scheduled to be tested | 2020-12-05 - Syncarpha Portfolio - Monthly Report, November, 2020.pdf
| Inverters/Model TBD | 2020-08-31 | Date when equipment is scheduled to be ordered | 2020-12-05 - Syncarpha Portfolio - Monthly Report, November, 2020.pdf
| Inverters/Model TBD | 2020-11-16 | Date when equipment is scheduled to be delivered | 2020-12-05 - Syncarpha Portfolio - Monthly Report, November, 2020.pdf
| Inverters/Model TBD | 2020-11-30 | Date when equipment is scheduled to be tested | 2020-12-05 - Syncarpha Portfolio - Monthly Report, November, 2020.pdf
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Solar | SMANG_00318 | 4
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Northbridge 2 - Batte
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-56 | 41179 | Syncarpha Northbridge 1 - Battery | Genbright LLC | 15140 | Syncarpha Northbridge 1 - Battery | Incremental Capacity | 2.222 | 2.222 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-05-22 | 2021-02-08 | 2021-02-26 | 2021-03-01 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Site Plan Approval | Town of Northbridge | MA | 2018-06-06 | 2018-07-10
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-05-18 | 2018-08-15
CPS - Financing | Source Name | Amount | Date Finance Secured
| Firstar Development | 468278 | 2019-06-01
| SPME Solar IV, LLC | 1337433 | 2019-01-01
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Battery | CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | 2020-06-22 | 2021-02-26
| Inverter | CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | 2020-06-22 | 2021-02-26
| Step Up Transformer | TBD | 2021-01-11 | 2021-02-22 | 2021-02-26
| Revenue Quality Meter | TBD | 2021-01-11 | 2021-02-22 | 2021-02-26
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Site Plan Approval/Town of Northbridge/MA | 2018-06-06 | Date when permit application is to be submitted | 2018-07-10 - Northbridge II - Site Plan Approval.pdf
| Site Plan Approval/Town of Northbridge/MA | 2018-07-10 | Date when permit application is to be approved | 2018-07-10 - Northbridge II - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-05-18 | Date when permit application is to be submitted | 2018-08-15 - Northbridge II - Order of Conditions (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-15 | Date when permit application is to be approved | 2018-08-15 - Northbridge II - Order of Conditions (Recorded).pdf
| Firstar Development/468278 | 2019-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge II Battery.pdf
| SPME Solar IV, LLC/1337433 | 2019-01-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge II Battery.pdf
| Battery/CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
| Battery/CS40HN-B2428-U-R1 (Battery) | 2020-06-22 | Date when equipment is scheduled to be delivered | 2019-12-23 - Independent Engineer Mechanical Completion Certificate - Northbridge II - DNV GL.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2020-06-22 | Date when equipment is scheduled to be delivered | 2019-12-23 - Independent Engineer Mechanical Completion Certificate - Northbridge II - DNV GL.pdf
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Battery | SMANG_00933 | 4
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Northbridge 2 - Solar
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-57 | 41183 | Syncarpha Northbridge 2 - Solar | Genbright LLC | 15141 | Syncarpha Northbridge 2 - Solar | Incremental Capacity | 2.765 | 0 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-05-22 | 2021-02-08 | 2021-02-26 | 2021-03-01 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Site Plan Approval | Town of Northbridge | MA | 2018-06-06 | 2018-07-10
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-05-18 | 2018-08-15
CPS - Financing | Source Name | Amount | Date Finance Secured
| Firstar Development | 5925676 | 2019-06-01
| SPME Solar IV, LLC | 10998447 | 2019-01-01
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Panels | Model #: SG60KU-M | 2019-07-01 | 2019-10-31 | 2020-07-03
| Inverter | TBD | 2019-07-01 | 2019-10-31 | 2020-07-03
| Step up Transformer | TBD | 2021-01-04 | 2021-02-15 | 2021-02-26
| Revenue Quality Meter | TBD | 2021-01-04 | 2021-02-15 | 2021-02-26
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Site Plan Approval/Town of Northbridge/MA | 2018-06-06 | Date when permit application is to be submitted | 2018-07-10 - Northbridge II - Site Plan Approval.pdf
| Site Plan Approval/Town of Northbridge/MA | 2018-07-10 | Date when permit application is to be approved | 2018-07-10 - Northbridge II - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-05-18 | Date when permit application is to be submitted | 2018-08-15 - Northbridge II - Order of Conditions (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-15 | Date when permit application is to be approved | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
| Firstar Development/5925676 | 2019-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge II Solar.pdf
| SPME Solar IV, LLC/10998447 | 2019-01-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Northbridge II Solar.pdf
| Panels/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
| Panels/Model #: SG60KU-M | 2019-10-31 | Date when equipment is scheduled to be delivered | 2019-12-23 - Independent Engineer Mechanical Completion Certificate - Northbridge II - DNV GL.pdf
| Panels/Model #: SG60KU-M | 2020-07-03 | Date when equipment is scheduled to be tested | 2019-12-23 - Independent Engineer Mechanical Completion Certificate - Northbridge II - DNV GL.pdf
| Inverter/TBD | 2019-07-01 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
| Inverter/TBD | 2019-10-31 | Date when equipment is scheduled to be delivered | 2019-12-23 - Independent Engineer Mechanical Completion Certificate - Northbridge II - DNV GL.pdf
| Inverter/TBD | 2020-07-03 | Date when equipment is scheduled to be tested | 2019-12-23 - Independent Engineer Mechanical Completion Certificate - Northbridge II - DNV GL.pdf
| SU Transformer/TBD | 2019-07-01 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
| Revenue Quality Meter/TBD | 2019-07-01 | Date when equipment is scheduled to be ordered | 2019-07-05 - Syncarpha Northbridge II - ENGIE - PO - (ARC PO#2019-008).pdf
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Solar | SMANG_00933 | 4.98
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Puddon 1 - Battery
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-60 | 41189 | Syncarpha Puddon 1 - Battery | Genbright LLC | 15144 | Syncarpha Puddon 1 - Battery | Incremental Capacity | 2.222 | 2.222 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-08-23 | 2020-11-23 | 2020-11-30 | 2020-12-01 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Special Permit | Town of Northbridge | MA | 2018-06-06 | 2018-08-14
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-06-13 | 2018-08-01
CPS - Financing | Source Name | Amount | Date Finance Secured
| Excelsior Renewable Energy Investment Fund 1 LP | 2696890 | 2019-06-14
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Battery | CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | 2020-06-12 | 2020-11-30
| Inverter | CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | 2020-06-12 | 2020-11-30
| Step Up Transformer | TBD | 2020-08-24 | 11/16/220 | 2020-11-30
| Revenue Quality Meter | TBD | 2020-08-24 | 11/16/220 | 2020-11-30
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Special Permit/Town of Northbridge/MA | 2018-06-06 | Date when permit application is to be submitted | 2018-07-12 - Puddon I - Site Plan Approval.pdf
| Special Permit/Town of Northbridge/MA | 2018-08-14 | Date when permit application is to be approved | 2018-07-12 - Puddon I - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-06-13 | Date when permit application is to be submitted | 2018-08-14 - Puddon I and II - Special Permit (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-01 | Date when permit application is to be approved | 2018-08-15 - Puddon I & II - Order of Conditions.pdf
| Excelsior Renewable Energy Investment Fund 1 LP/2696890 | 2019-06-14 | Date when funding is scheduled to be secured. | ISO-NE Financing Letter_Puddon I Battery_DRAFT.docx
| Battery/CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Battery/CS40HN-B2428-U-R1 (Battery) | 2020-06-12 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2020-06-12 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Step Up Transformer/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Revenue Quality Meter/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Substantial Site Construction | 2020-11-23 | Substantial Site Construction | Construction Quarterly Update
| Commissioning Completion Date | 2020-11-30 | Commissioning Completion Date | Construction Quarterly Update
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Battery | SMANG_00046 | 4
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Puddon 1 - Solar
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-59 | 41187 | Syncarpha Puddon 1 - Solar | Genbright LLC | 15143 | Syncarpha Puddon 1 - Solar | Incremental Capacity | 2.764 | 0 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2017-11-17 | 2020-11-23 | 2020-11-30 | 2020-12-01 | text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Site Plan Approval | Town of Northbridge | MA | 2018-06-06 | 2018-07-10
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-06-13 | 2018-08-01
CPS - Financing | Source Name | Amount | Date Finance Secured
| Excelsior Renewable Energy Investment Fund 1 LP | 22500000 | 2019-06-14
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Panels | Model #: SG60KU-M | 2019-07-01 | 2019-10-31 | 2020-11-30
| Inverter | Model #: SG60KU-M | 2019-07-01 | 2019-10-31 | 2020-11-30
| Step Up Transformer | TBD | 2020-08-24 | 2020-11-23 | 2020-11-30
| Revenue Quality Meter | TBD | 2020-08-24 | 2020-11-23 | 2020-11-30
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Site Plan Approval/Town of Northbridge/MA | 2018-06-06 | Date when permit application is to be submitted | 2018-07-12 - Puddon I - Site Plan Approval.pdf
| Site Plan Approval/Town of Northbridge/MA | 2018-07-10 | Date when permit application is to be approved | 2018-07-12 - Puddon I - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-06-13 | Date when permit application is to be submitted | 2018-08-14 - Puddon I and II - Special Permit (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-01 | Date when permit application is to be approved | 2018-08-15 - Puddon I & II - Order of Conditions.pdf
| Excelsior Renewable Energy Investment Fund 1 LP/22500000 | 2019-06-14 | Date when funding is scheduled to be secured. | ISO-NE Financing Letter_Puddon I Solar.pdf
| Panels/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Panels/Model #: SG60KU-M | 2019-10-31 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Inverter/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Inverter/Model #: SG60KU-M | 2019-10-31 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Step Up Transformer/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Revenue Quality Meter/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon I.pdf
| Substantial Site Construction | 2020-11-23 | Substantial Site Construction | Registered and mapped to resource in CAMS
| Commissioning Completion Date | 2020-11-30 | Commissioning Completion Date | Registered and mapped to resource in CAMS
| Commercial Operations Date | 2020-12-01 | Commercial Operations Date | Registered and mapped to resource in CAMS
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Solar | SMANG_00046 | 4.98
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Puddon 2 - Battery
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-62 | 41193 | Syncarpha Puddon 2 - Battery | Genbright LLC | 15146 | Syncarpha Puddon 2 - Battery | Incremental Capacity | 2.222 | 2.222 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-08-23 | 2020-11-16 | 2020-11-30 | 2020-12-01 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Special Permit | Town of Northbridge | MA | 2018-06-06 | 2018-08-14
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-06-13 | 2018-08-01
CPS - Financing | Source Name | Amount | Date Finance Secured
| Excelsior Renewable Energy Investment Fund 1 LP | 2696890 | 2019-06-14
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Battery | CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | 2020-06-12 | 2020-11-30
| Inverter | CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | 2020-06-12 | 2020-11-30
| Step Up Transformer | TBD | 2020-08-24 | 2020-11-16 | 2020-11-30
| Revenue Quality Meter | TBD | 2020-08-24 | 2020-11-16 | 2020-11-30
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Special Permit/Town of Northbridge/MA | 2018-06-06 | Date when permit application is to be submitted | 2018-07-12 - Puddon II - Site Plan Approval.pdf
| Special Permit/Town of Northbridge/MA | 2018-08-14 | Date when permit application is to be approved | 2018-07-12 - Puddon II - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-06-13 | Date when permit application is to be submitted | 2018-08-14 - Puddon I and II - Special Permit (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-01 | Date when permit application is to be approved | 2018-08-15 - Puddon I & II - Order of Conditions.pdf
| Excelsior Renewable Energy Investment Fund 1 LP/2696890 | 2019-06-14 | Date when funding is scheduled to be secured. | ISO-NE Financing Letter_Puddon II Battery_DRAFT.docx
| Battery/CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Battery/CS40HN-B2428-U-R1 (Battery) | 2020-06-12 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2020-06-12 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Step Up Transformer/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Revenue Quality Meter/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Substantial Site Construction | 2020-11-16 | Substantial Site Construction | Construction Quarterly Update
| Commissioning Completion Date | 2020-11-30 | Commissioning Completion Date | Construction Quarterly Update
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Battery | SMANG_00066 | 4
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Puddon 2 - Solar
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-61 | 41191 | Syncarpha Puddon 2 - Solar | Genbright LLC | 15145 | Syncarpha Puddon 2 - Solar | Incremental Capacity | 2.764 | 0 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2018-08-23 | 2020-11-16 | 2020-11-30 | 2020-12-01 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Site Plan Approval | Town of Northbridge | MA | 2018-06-06 | 2018-07-10
| Order of Conditions | Town of Northbridge Conservation Commission | MA | 2018-06-13 | 2018-08-01
CPS - Financing | Source Name | Amount | Date Finance Secured
| Excelsior Renewable Energy Investment Fund 1 LP | 23000000 | 2019-06-14
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Panels | Model #: SG60KU-M | 2019-07-01 | 2019-10-31 | 2020-11-30
| Inverter | Model #: SG60KU-M | 2019-07-01 | 2019-10-31 | 2020-11-30
| Step Up Transformer | TBD | 2020-08-24 | 2020-11-16 | 2020-11-30
| Revenue Quality Meter | TBD | 2020-08-24 | 2020-11-16 | 2020-11-30
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Site Plan Approval/Town of Northbridge/MA | 2018-06-06 | Date when permit application is to be submitted | 2018-07-12 - Puddon II - Site Plan Approval.pdf
| Site Plan Approval/Town of Northbridge/MA | 2018-07-10 | Date when permit application is to be approved | 2018-07-12 - Puddon II - Site Plan Approval.pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-06-13 | Date when permit application is to be submitted | 2018-08-14 - Puddon I and II - Special Permit (Recorded).pdf
| Order of Conditions/Town of Northbridge Conservation Commission/MA | 2018-08-01 | Date when permit application is to be approved | 2018-08-15 - Puddon I & II - Order of Conditions.pdf
| Excelsior Renewable Energy Investment Fund 1 LP/23000000 | 2019-06-14 | Date when funding is scheduled to be secured. | ISO-NE Financing Letter_Puddon II Solar_DRAFT.docx
| Panels/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Panels/Model #: SG60KU-M | 2019-10-31 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Inverter/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Inverter/Model #: SG60KU-M | 2019-10-31 | Date when equipment is scheduled to be delivered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Step Up Transformer/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Revenue Quality Meter/TBD | 2020-08-24 | Date when equipment is scheduled to be ordered | EEC-Sol - IE Mechanical Completion Certificate - Puddon II.pdf
| Substantial Site Construction | 2020-11-16 | Substantial Site Construction | Registered and mapped to resource in CAMS
| Commissioning Completion Date | 2020-11-30 | Commissioning Completion Date | Registered and mapped to resource in CAMS
| Commercial Operations Date | 2020-12-01 | Commercial Operations Date | Registered and mapped to resource in CAMS
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Solar | SMANG_00066 | 4.98
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Tewksbury - Storage
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-64 | 41200 | Syncarpha Tewksbury - Storage | Genbright LLC | 15148 | Syncarpha Tewksbury - Storage | Incremental Capacity | 1.111 | 1.111 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2017-11-02 | 2021-05-15 | 2021-05-02 | 2021-05-31 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Special Permit | Town of Tewksbury Planning Board | MA | 2018-10-23 | 2018-11-13
| Order of Conditions | Town of Tewksbury Conservation Commission | MA | 2018-11-01 | 2018-11-21
CPS - Financing | Source Name | Amount | Date Finance Secured
| Milliken Design, Inc | 305909 | 2019-06-01
| SPME Solar IV, LLC | 939106 | 2019-06-01
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Battery | CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | 2021-02-26 | 2021-05-27
| Inverter | CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | 2021-02-26 | 2021-05-27
| Step Up Transformer | TBD | 2021-01-25 | 2021-04-19 | 2021-05-27
| Revenue Quality Meter | TBD | 2021-01-25 | 2021-04-19 | 2021-05-27
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Special Permit/Town of Tewksbury Planning Board/MA | 2018-10-23 | Date when permit application is to be submitted | 2018-11-13 - Tewksbury - Special Permit.pdf
| Special Permit/Town of Tewksbury Planning Board/MA | 2018-11-13 | Date when permit application is to be approved | 2018-11-13 - Tewksbury - Special Permit.pdf
| Order of Conditions/Town of Tewksbury Conservation Commission/MA | 2018-11-01 | Date when permit application is to be submitted | Financing Letter - Syncarpha Tewksbury Solar.pdf
| Order of Conditions/Town of Tewksbury Conservation Commission/MA | 2018-11-21 | Date when permit application is to be approved | 2018-11-26 - Order of Conditions - Syncarpha Tewksbury - Recorded.pdf
| Milliken Design, Inc/305909 | 2019-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Tewksbury Storage.pdf
| SPME Solar IV, LLC/939106 | 2019-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Tewksbury Storage.pdf
| Battery/CS40HN-B2428-U-R1 (Battery) | 2019-07-03 | Date when equipment is scheduled to be ordered | MA_SMART_PO_(Syncarpha_Tewksbury)_July_SSA_ENGIE_(FINAL)_20190705 FE.pdf
| Inverter/CS10HN-P1000-U-R1 (Inverter) | 2019-07-03 | Date when equipment is scheduled to be ordered | MA_SMART_PO_(Syncarpha_Tewksbury)_July_SSA_ENGIE_(FINAL)_20190705 FE.pdf
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Battery | SMANG_00309 | 2
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a

## Syncarpha Tewksbury - Solar
Lead Market Participant Project Data
Resource Details | Internal Checklist ID | Resource ID | Name | Lead Participant | Proposal ID | Project Name | Project Type | Claimed Summer MW | Claimed Winter MW | FERC
| FCA16-63 | 41196 | Syncarpha Tewksbury - Solar | Genbright LLC | 15147 | Syncarpha Tewksbury - Solar | Incremental Capacity | 1.577 | 0 | Non-FERC
Elections | Commitment Period Election (1-7)* | Rationing Election (Ecomin)* | Rationing Amount*
| 1 | Yes | 0.1
Substitution Auction | SA Election* | SA Certification Document* | Document Description*
| Yes | SPR-Cert_Genbright_FCA_16.PDF | Substitution Auction Certification
Developer - Critical Path Schedule Data Request
CPS - Critical Dates | Interconnection Request Submission Date | Substantial Site construction Date | Commissioning Completion Date | COD* | Additional Information Description |  | Note:Examples of Acceptable Data provided in Italics
| 2017-11-02 | 2021-05-01 | 2021-05-03 | 2021-05-12 | Text
Critical Path Schedule - Major Permits | Permit Name | Agency | State/ Locality | Application Date | Approval Date
| Special Permit | Town of Tewksbury Planning Board | MA | 2018-10-23 | 2018-11-13
| Order of Conditions | Town of Tewksbury Conservation Commission | MA | 2018-11-01 | 2018-11-21
CPS - Financing | Source Name | Amount | Date Finance Secured
| Milliken Design, Inc | 2586446 | 2019-06-01
| SPME Solar IV, LLC | 5353651 | 2019-01-01
CPS - Major Equipment | Manufacturer | Model/ Identifier | Order Date | Delivery Date | Test Completion Date
| Panels | Model #: SG60KU-M | 2019-07-01 | 2020-08-01 | 2021-03-09
| Inverter | Model #: SG60KU-M | 2019-07-01 | 2020-08-01 | 2021-03-09
| Step Up Transformer | TBD | 2021-01-25 | 2021-04-05 | 2021-04-30
| Revenue Quality Meter | TBD | 2021-01-25 | 2021-04-05 | 2021-04-30
CPS Completed Milestones - Major Permits - Financing - Equipment - Other | Description | Milestone Date | Milestone Type | Documentation Upload
| Special Permit/Town of Tewksbury Planning Board/MA | 2018-10-23 | Date when permit application is to be submitted | 2018-11-13 - Tewksbury - Special Permit Pg1-7.pdf
| Special Permit/Town of Tewksbury Planning Board/MA | 2018-11-13 | Date when permit application is to be approved | 2018-11-13 - Tewksbury - Special Permit Pg1-7.pdf
| Order of Conditions/Town of Tewksbury Conservation Commission/MA | 2018-11-01 | Date when permit application is to be submitted | 2018-11-26 - Order of Conditions - Syncarpha Tewksbury - Recorded.pdf
| Order of Conditions/Town of Tewksbury Conservation Commission/MA | 2018-11-21 | Date when permit application is to be approved | 2018-11-26 - Order of Conditions - Syncarpha Tewksbury - Recorded.pdf
| Milliken Design, Inc/2586446 | 2019-06-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Tewksbury Solar.pdf
| SPME Solar IV, LLC/5353651 | 2019-01-01 | Date when funding is scheduled to be secured. | Financing Letter - Syncarpha Tewksbury Solar.pdf
| Panels/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | MA_SMART_PO_(Syncarpha_Tewksbury)_July_SSA_ENGIE_(FINAL)_20190705 FE.pdf
| Panels/Model #: SG60KU-M | 2020-08-01 | Date when equipment is scheduled to be delivered | Sync - Tewksbury PVsyst.pdf
| Inverter/Model #: SG60KU-M | 2019-07-01 | Date when equipment is scheduled to be ordered | MA_SMART_PO_(Syncarpha_Tewksbury)_July_SSA_ENGIE_(FINAL)_20190705 FE.pdf
| Inverter/Model #: SG60KU-M | 2020-08-01 | Date when equipment is scheduled to be delivered | Sync - Tewksbury PVsyst.pdf
Developer - Renewable Resource State Subsidy Information
Substitution Auction | NEPOOL GIS Unit ID | Technology Type | RPS/CES/APS ID# | RPS/CES/APS MW
| # | Solar | SMANG_00309 | 2.838
Lead Market Participant Additional Data
Additional Requirements - Intermittent | Document Date | Document Description Site Specific Data | File name
| TBD | TBD | TBD
| Document Date | Document Description - Claimed Capability Workbook | File name
| n/a | n/a | n/a
Additional Requirements for Incremental Projects | Manufacturer | Model # /Identifier | Cost
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
| n/a | n/a | n/a
CPS - Other Supporting Documents | Documentation Upload + Fuel Survey | Document Description
| n/a | n/a